## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Introduction to project | MUST HAVE | No dependency | Sai Pujitha,Sibi Shree, Subiksen, Divi Venkateswara Rao | 3- Completed
S1 | S1 | US-001 | Research and explore suitable datasets for ticket analysis (e.g., Hugging Face – Customer Support Tickets) | MUST HAVE | No dependency | Sai Pujitha,Sibi Shree, Subiksen, Divi Venkateswara Rao | 3- Completed
S1 | S1 | US-001 | Collect and clean ticket data from the Hugging Face dataset to prepare for model training. | MUST HAVE | No dependency | Kunjeti Sai Pujitha | 3- Completed
S1 | S1 | US-001 | Categorize tickets into High, Medium, and Low priority levels. | MUST HAVE | Cleaned dataset | Sai Pujitha, Sibi Shree | 3- Completed
S2 | S2 | US-001 | Generate sentence embeddings using the MiniLM model for semantic understanding of tickets. | MUST HAVE | Cleaned and categorized dataset | Sai Pujitha | 3- Completed
S2 | S2 | US-001 | Develop a recommendation module that suggests related articles using MiniLM embeddings. | MUST HAVE | Embeddings must be generated | Sibi Shree | 3- Completed
S2 | S2 | US-001 | Integrate the recommendation system with the frontend (Streamlit UI) to display results. | SHOULD HAVE | Recommendation logic must be implemented. | Divi Venkateswara Rao | 3- Completed
S3 | S3 | US-001 | Replace MiniLM-based retrieval with FAISS vector search for faster and more accurate recommendations. | MUST HAVE | MiniLM model and embeddings must exist. | Sai Pujitha | 3- Completed
S3 | S3 | US-001 | Implement content gap detection using BERTopic/LDA to identify missing knowledge areas. | SHOULD HAVE | FAISS-based recommendation pipeline should be functional. | Subiksen | 3- Completed
S4 | S4 | US-001 | Build an analytics dashboard using Streamlit/Seaborn to visualize performance and gaps. | MUST HAVE | Gap detection and FAISS outputs finalized. | Divi Venkateswara Rao | 3- Completed
S4 | S4 | US-001 | Generate automatic gap alerts based on analysis results to flag new article needs. | MUST HAVE | Dashboard setup and alert logic. | Sai Pujitha | 3- Completed
S4 | S4 | US-001 | Allow the admin to update solutions for tickets that have content gaps. | MUST HAVE | Gap detection | Sai Pujitha | 3- Completed
S4 | S4 | US-001 | Integrate Slack API to send real-time notifications for detected gaps and updates. | SHOULD HAVE | Auto-gap alert system functional. | Sibi Shree | 3- Completed
S4 | S4 | US-001 | Prepare final project performance report summarizing accuracy, response time, and findings. | MUST HAVE | Dashboard and Slack integration functional. | Sai Pujitha, Sibi Shree, Subiksen, Divi Venkateswara Rao | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 248 | 124 | 124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | T1 | Collect and clean customer ticket dataset | 2024-10-10 | 2024-10-12 | Sai Pujitha | Data Cleaning | Completed | 16 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | T2 | Create database schema and setup SQLite storage | 2024-10-11 | 2024-10-14 | Sibi Shree | Database Setup | Completed | 20 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | T3 | Insert dataset into database with validation | 2024-10-13 | 2024-10-18 | Subiksen | Data Insertion | Completed | 24 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 2 BACKLOG
US-004 | T4 | Create embedding pipeline using MiniLM model | 2024-10-19 | 2024-10-21 | Sai Pujitha | Feature Extraction | Completed | 20 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | T5 | Implement data preprocessing with token cleaning | 2024-10-20 | 2024-10-23 | Divi | Preprocessing | Completed | 16 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | T6 | Automate embedding storage and retrieval | 2024-10-22 | 2024-10-25 | Sibi Shree | Backend Automation | Completed | 24 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 3 BACKLOG
US-007 | T7 | Implement topic modeling using BERTTopic | 2024-10-26 | 2024-10-28 | Subiksen | NLP Modeling | Completed | 24 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-008 | T8 | Compare BERTTopic with LDA and analyze coherence | 2024-10-27 | 2024-10-30 | Divi | Model Evaluation | Completed | 20 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-009 | T9 | Generate summary insights from key topics | 2024-10-30 | 2024-11-02 | Sibi Shree | Report Generation | Completed | 16 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 4 BACKLOG
US-010 | T10 | Build API for ticket update and substatus tracking | 2024-11-03 | 2024-11-05 | Sibi Shree | API Development | Completed | 20 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-011 | T11 | Integrate Slack alert system for priority tickets | 2024-11-05 | 2024-11-08 | Sai Pujitha | Automation | Completed | 24 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-012 | T12 | Design and deploy analytics dashboard | 2024-11-08 | 2024-11-12 | Divi | Visualization | Completed | 24 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
S1 | Day 2 | Minor delay in dataset exploration due to large size of Hugging Face dataset. | Filtered only relevant columns (ticket body & priority). Used pandas for data cleaning and reduced dataset size for efficiency.
S1 | Day 4 | Some tickets lacked priority labels (missing values). | Assigned “Low” by default and standardized priority names.
S2 | Day 3 | High memory usage during MiniLM embedding generation. | Switched to batch processing and used a smaller sentence transformer model for optimization.
S2 | Day 5 | Integration between recommendation logic and Streamlit UI faced compatibility issues. | Updated Streamlit version and refactored code to align data flow between backend & frontend.
S3 | Day 2 | FAISS installation issues on Windows environment. | Created a virtual environment and installed using compatible binary wheel (faiss-cpu).
S3 | Day 4 | BERTopic model required GPU for faster topic detection. | Used Google Colab with GPU runtime for model execution and exported topic results.
S4 | Day 2 | Slack API rate limits occasionally delayed notifications. | Implemented delay queue and batched message updates to comply with Slack API limits.
S4 | Day 4 | Dashboard visualization errors due to mismatched dataframe columns. | Standardized schema across modules and tested Seaborn plots with sample data before full integration.
S4 | Day 6 | Final performance report formatting issues (table overflow in Streamlit). | Adjusted layout using st.dataframe() and column width control to improve readability.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | S1 | 2024-10-10 | 2024-10-18 | Sai Pujitha, Sibi Shree | Explore and clean customer ticket datasets | Relying only on manual data validation | Collaborative dataset cleaning and prioritization | Successfully built and cleaned initial Hugging Face dataset
2 | S2 | 2024-10-19 | 2024-10-25 | Sai Pujitha, Sibi Shree | Automate sentence embedding creation using MiniLM | Running embeddings sequentially (slow) | Working in pairs for model optimization and code review | Optimized embedding and recommendation module
3 | S3 | 2024-10-26 | 2024-11-02 | Subiksen, Divi | Implement BERTTopic/LDA for content gap detection | Manual tagging of missing content | Using Streamlit for frontend testing and visualization | Completed FAISS integration and topic modeling
4 | S4 | 2024-11-03 | 2024-11-12 | Sai Pujitha, Sibi Shree, Divi | Automate Slack alerts and analytics dashboard | Manual reporting of findings | Collaborative dashboard refinement and automation | Delivered analytics dashboard and automated alert system